# Oregon Joint Use Association

Publicity and Education Committee

December 12, 2013

Comcast Office - 11308 SW 68th Parkway Tigard

# Call to Order

Meeting called to order by Jerry at 10:11 am.

Present: Jerry Donovan, Tal Nelson, Jesse Martin, Dawna Farrell, Tom Jorgenson

Excused: Mark Sanford, Jeff VanLoo, Steve Ross

Staff: Jessica Carpenter

# Approval of Minutes

Review minutes of November 12, 2013 – Motion by Jesse Martin, 2nd by Tal Nelson approved with no changes.  Motion Passed.

Chair Report

- Chair Donovan reported that he had discussed with the OJUA Board the idea that the committee would like to reduce or remove the underground portion of the Spring Training.  The Board agreed that this area could be a smaller part of the Spring Training.  Chair Donovan will discuss this change with Speaker David Marne.

- Discuss Spring Training Timeline – are updates needed?

Task						Target Date

Speaker(s) recommendation to Board		August 1, 2013 – completed

Lockdown of Speaker(s)			September 1, 2013 – completed

Begin Photo Review				October 14, 2013 – in progress

Lockdown of Categories			November 14, 2013 – in progress

Electronic save-the-date flyer distributed		November 15, 2013 - completed

Lockdown of Agenda 				December 12, 2013

Deadline for photos to Committee		December 12, 2013

Questions to Committee				December 12, 2013

Draft of games completed			January 9, 2014

Draft Registration form due 			January 10, 2014

Registration form out 				January 25, 2014

Monthly e-blast reminder through March 15	monthly starting in November

Finalize Question/Photos			February 1, 2014

Determine giveaway 				February 2014 Meeting

Order giveaway 				February 28, 2014

Draft of game completed 			March 1, 2014

Jeopardy Team presents test run			March P&E Meeting

Final facility inspection & walk-through		March 1, 2014

Early bird price expires 				March 14, 2014

Weekly e-blast reminder starting March 15 	March 15, 2014

Game completed and tested			February 6, 2014

Focus on logistics				March 23 – April 21, 2014

Jeopardy Working Session

Reviewed progress of the Jeopardy game, discussed ideal AV needs and staff will check with Embassy Suites on availability and pricing.  Staff requested room layout from Embassy Suites and shared with Chair Donovan and Tal Nelson for set up potential.

Meeting adjourned at 12:11pm

Next Meeting

When – January 9, 2014

Where – Comcast in Tigard

Time – 10am – Noon (unless changed)

#### Adjourn

Meeting adjourned at _________.