# Oregon Joint Use Association

Publicity and Education Committee Meeting Minutes

November 12, 2013

# Call to Order

Meeting called to order by Chair Donovan at 10:14 am.

Present: Jerry Donovan, Jeff Van Loo, Steve Ross, Jesse Martin, Tal Nelson, Dawna Farrell

Excused: Tom Jorgenson, Tory Robinson, Mark Sanford

Staff: Laureal Williams

# Approval of Minutes

Review minutes of October 14, 2013 – Moved by Jeff Van Loo, seconded by Dawna Farrell, to approve the minutes of the October 14 meeting.  Motion passed.

Chair Report

- The committee reviewed the 2014 meeting/event calendar; most P & E Committee meetings are currently scheduled for the second Thursday of each month.  Two corrections were noted and staff was asked to move the February meeting to the first Thursday.

- The committee discussed a tentative daily schedule for the Spring Training event:

  - Day One: NESC Code Book, Lunch, Jeopardy, NESC Code Book.

  - Day Two: Jeopardy, NESC Code Book, Lunch, Industry Slang, Mythbusters

Chair Donovan agreed to discuss the daily schedule with presenter David Marne, including the possibility of removing the topics of underground and station maintenance from the NESC Codebook presentation.

- In reviewing storage options for the Jeopardy presentation, Tal reported that he has implemented a Dropbox system for housing photos, questions, and other supporting materials as appropriate.

- The committee reviewed and updated the Spring Training Timeline as follows (revisions noted in bold font)

Task						Target Date

Speaker(s) recommendation to Board		August 1, 2013 – completed

Lockdown of Speaker(s)			September 1, 2013 – completed

Begin Photo Review				October 14, 2013 – in progress

Lockdown of Categories			November 14, 2013 – in progress

Electronic save-the-date flyer distributed		November 15, 2013 – in progress

Monthly e-blast reminder through March 15	monthly starting in November

Lockdown of Agenda 				December 12, 2013

Deadline for photos to Committee		December 12, 2013

Questions to Committee			December 12, 2013

Provide giveaway options to committee	December 12, 2013

Draft of games completed			January 9, 2014 (working session)

Start discussion of giveaway			January 9, 2014

Draft Registration form due 			January 10, 2014

Registration form out 				January 24, 2014

Finalize Question/Photos			February 6, 2014 (working session)

Determine giveaway 				February 6, 2014

Order giveaway 				February 7, 2014

Weekly e-blast reminder starting		February 17, 2014

Early bird price expires 			February 28, 2014

Jeopardy Team presents test run		March 13, 2014

Final facility inspection & walk-through	TBD, March 2014

Focus on logistics				March 23 – April 21, 2014

New Business

It was the consensus of the committee to begin working on Mythbusters and Industry Slang presentations via email in order to determine what level of effort will be needed to prepare these presentations for the Spring Training.  Tal indicated that he would add folders to the existing Dropbox for these presentations.

Jeopardy Working Session

The committee reviewed the basic format of the Jeopardy presentation, informally discussing items such as daily doubles and response timelines (by consensus, two minutes seemed appropriate for).  The committee determined that staff should be responsible for designating the Jeopardy teams, with a focus on blending the makeup of teams between power and communications to encourage networking and distributing out the participants with greater NESC experience in an effort to avoid one or two “stacked teams.”

Adjourn

With no further business to discuss, Chair Donovan adjourned the meeting at 1:03 p.m.

Next Meeting

When – December 12, 2013, Bring Code Book

Where – Comcast in Tigard

Time – 10am – Noon (unless changed)